## Backlog1
PBI | Task | Time | Task In Progress | Name | Completed Task | Name
Ability to enter a filename that does not exist, and have the election re-prompt the user | Update BallotHandler to keep re-prompting the user for filenames if they enter an incorrect file name | 0.5 hours |  |  | Modify BallotHandler to skip ballot creation in the case that 60% of the candidates are not ranked, in the case that the ballots are for STV. | Joe
Ability to run a Municipal Voting (MV) election | Create and implement MVElection class in the source code and header files | 1.5 hours |  |  | Create and implement MVElection class in the source code and header files | Ben
Ability to run a Municipal Voting (MV) election | Unit test the MVElection class and ensure all tests pass | 1 hour |  |  | Add a std out call at the end of the Municipal Voting election class that prints out the details regarding the Municipal Voting election results | Ben
Ability to run a Municipal Voting (MV) election | Document MVElection class | 0.5 hours |  |  | Update BallotHandler to keep re-prompting the user for filenames if they enter an incorrect file name | Adam
Ability to use a CSV file with Municipal Voting (MV) election ballots in it | Update BallotHandler class to handle MV election ballots | 0.5 hours |  |  | Add functionality in BallotHandler class that parses headers in CSV files, so that all types of elections can be run without user interaction aside from entering file names | Joe
Ability to use a CSV file with Municipal Voting (MV) election ballots in it | Update BallotHandler unit tests to cover MV election ballots | 0.25 hours |  |  | Add Ballot removal logic coverage to unit tests, and ensure that they pass. | Joe
Ability to bring all of the election information from the header of the .csv file | Add functionality in BallotHandler class that parses headers in CSV files, so that all types of elections can be run without user interaction aside from entering file names | 1 hour |  |  | Unit test the MVElection class and ensure all tests pass | Ben
Ability to bring all of the election information from the header of the .csv file | Update BallotHandler unit tests to cover CSV header parsing logic | 0.5 hours |  |  | Document MVElection class | Ben
Ensure all ballots have 60% of candidates ranked for an STV election. | Modify BallotHandler to skip ballot creation in the case that 60% of the candidates are not ranked, in the case that the ballots are for STV. | 1 hour |  |  | Update BallotHandler class to handle MV election ballots | Quang
Ensure all ballots have 60% of candidates ranked for an STV election. | Add Ballot removal logic coverage to unit tests, and ensure that they pass. | 1 hour |  |  | Update BallotHandler unit tests to cover CSV header parsing logic | Joe
Ensure invalidated ballots are added to a file | Modify BallotHandler to add all of the thrown-out ballots from the 60% task to a separate CSV file. | 1 hour |  |  | Update BallotHandler unit tests to cover MV election ballots | Quang
Ensure invalidated ballots are added to a file | Add a unit test to ensure that the file has been properly created and populated with the thrown-out ballots. | 1 hour |  |  | Add a unit test to ensure that the file has been properly created and populated with the thrown-out ballots. | Adam
Report MV to screen | Add a std out call at the end of the Municipal Voting election class that prints out the details regarding the Municipal Voting election results | 0.25 hour |  |  | Modify BallotHandler to add all of the thrown-out ballots from the 60% task to a separate CSV file. | Adam

## Backlog2
PBI | Task | Time | Task In Progress | Name | Completed Task | Name
MV Audit report | Add Functionality to create MV Audit Report | 1 hour |  |  | MV Audit report | Ben
Integrate Parts | Meet and integrate all parts to make a single working election program | 2 hours | Meet and integrate all parts to make a single working election program | Quang
Select files via a directory GUI | Allow CSV files to be selected by clicking in GUI instead of typing in file names | 2 hours | Allow CSV files to be selected by clicking in GUI instead of typing in file names | Adam
Select files via a directory GUI | Refactor BallotHandler to accept the CSV files via GUI selections | 1 hour | Refactor BallotHandler to accept the CSV files via GUI selections | Adam
Integrate Parts | Update system testing to cover updates after integration | 1 hour | Update system testing to cover updates after integration | Joe
MV Audit report | Add MV audit report coverate to unit tests | 0.5 hours
Select files via a directory GUI | Unit test GUI file selection | 1 hour